## Outline
Summary: The main idea is to use surface weather station data to characterise the strength of the sea-breeze oscillation over Indonesian islands and to investigate how sea-breeze varies during MJO events
Start Day | End day | Description | Duration (Days)
2016-06-13 | 2016-06-14 | Completion of background reading | 2
2016-06-13 | 2016-06-13 | Creating a map to visualise the locations of AWS | 1
2016-06-14 | 2016-06-15 | Filtering out DJF data from AWS using Vi | 2
2016-06-15 | 2016-06-17 | U and V wind rotation and angle calculation | 3
2016-06-17 | 2016-06-20 | Verifying wind component scripts – original and rotated | 4
2016-06-20 | 2016-06-22 | Using rotated wind angles and MATLAB to process DJF raw data and identify suitable stations based on mean diurnal cycle of onshore/offshore wind | 3
2016-06-25 | 2016-06-27 | Summarising on Excel different categories of station suitability, and also visually on a map | 3
2016-06-27 | 2016-06-29 | Using the best AWS station data from 2005-2015 to develop plots for each station on average diurnal cycle based on each of the 8 MJO phases | 3
2016-06-13 | 2016-07-01 | Reflections (on-going) – includes scanning hand-drawn figures for work record | 16 | (Can include time in DC)
2016-06-27 | 2016-07-01 | REPORT (on-going) | 5 | (Can include time in DC)
UGRL Plan for Year 1 – first half (13 June to 1 July)
NB: Start day: 13/6/16 to 1/7/16 (and conferences on 4-6 July)
Then 5/9/16 - 23/9/16
Total of 28 working days - back ups in weekends on during time in DC
Report is due on 20/9/16
Data – must wait to receive as application was filled in this morning!
*Days 9 and 10 were outward bound. Day 10 started on Saturday when I came in to the office to work an extra few hours

## Chart 1
Tasks
Start Date | End Date | Description | Duration (Days)
2016-06-13 | 2016-06-14 | Complete background reading | 2
2016-06-13 | 2016-06-13 | Create a map to visualise the locations of AWS | 1
2016-06-14 | 2016-06-15 | Filter out DJF data for 2003-2016 from AWS using Vi | 2
2016-06-15 | 2016-06-17 | U and V wind rotation and angle calculation for all 137 stations - calculate onshore wind | 3
2016-06-17 | 2016-06-20 | Verify wind component scripts – original and rotated | 4
2016-06-20 | 2016-06-22 | Data quality assessment: use rotated wind angles and MATLAB to process DJF raw data and identify suitable stations based on mean diurnal cycle of onshore/offshore wind | 3
2016-06-25 | 2016-06-27 | Summarise on Excel different categories of station suitability, and also visually on a map | 3
2016-06-27 | 2016-07-01 | Use the best AWS station data from 2005-2015 to plot average diurnal cycle of onshore (v) wind and sea breeze based on each MJO phases for each station | 5
2016-06-13 | 2016-07-01 | Reflections (on-going) – includes scanning hand-drawn figures for work record | 19
2016-06-27 | 2016-07-01 | Report (on-going) | 5

## Chart 2
Tasks
Start Date | End Date | Description | Duration (Days)
2016-09-05 | 2016-09-08 | Data quality checks for all stations, including those with good data from 2010 | 3
2016-09-07 | 2016-09-09 | MJO phase vs sea breeze plot within the domain in Birch et al. square (fig 1) | 2
2016-09-09 | 2016-09-12 | Check for difference in MJO phase vs sea breeze east and west of the domain used and split/average stations in to 3 sectors | 3
2016-09-09 | 2016-09-09 | Incorporate Birch et al figure 11 lines into MJO phase vs sea breeze plot | 1
2016-09-13 | 2016-09-14 | Plot the mean diurnal cycle of temperature by MJO phase to explain why sea breeze strength varies by MJO phase | 1
2016-09-16 | 2016-09-19 | Cross-correlation to compare lag of MJO onset for each sector | 4 | 2016-09-13 | Plot land-averaged rainfall (daily mean and mean diurnal cycle) - NOT INCLUDED IN EMAIL but this was Simon Peatman's proposal | 0
2016-09-15 | 2016-09-20 | Analysis of model data from Birch et al paper to show motivation for sea breeze vs MJO rainfall | 3 | 2016-09-15 | Plot low-level wind convergence and rainfall to demonstrate link between MJO, sea breeze, and rainfall - POSSIBLE | 0
2016-09-05 | 2016-09-23 | Reflections (on-going) – including important figures | 18
2016-09-10 | 2016-09-20 | Report (on-going) | 10
2016-09-10 | 2016-09-23 | Presentation (on-going) | 13
2016-09-10 | 2016-09-20 | Donor's letter | 10